## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
The dashboard UI was clean, responsive, and well-received during stakeholder demos. | Behavioral trend filtering had several edge-case failures in early testing. | Implement automated edge-case testing for data-driven filters. | Add unit tests with mock data for all filter ranges in the next sprint.
Communication between developers and designers was smooth, preventing UI conflicts. | Report export function initially failed under load. | Use background job queues for handling exports. | Integrate serverless report generation via AWS Lambda.
Clear sprint goals helped the team stay focused and complete all planned stories. | Incomplete test coverage for socio-economic insights module. | Involve QA earlier during the design stage. | Schedule QA walkthroughs during the first week of each sprint.
The role model impact chart was praised for clarity and interactivity. | Some confusion around tooltips caused misinterpretation of data. | Improve tooltip clarity and add small “info” icons for context. | Involve UX writer to review tooltip content in the design phase.
Collaboration tools (like Git branching strategy and shared Figma) were used effectively. | Peer reviews were skipped due to time pressure during crunch hours. | Make code reviews mandatory before merging to main branch. | Enforce branch protection rules and review assignment.