## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
Example : All tasks were completed on time. Team communication was seamless. | Requirements changed mid-sprint. | Plan for a buffer to handle scope changes. | Set stricter deadlines for finalizing requirements. | Example
Mentor matching algorithm MVP launched successfully. | Algorithm’s "Top 3 Matches" had low user acceptance rates. | Incorporate user feedback into matching logic (e.g., preference weighting). | Incorporate user feedback into matching logic (e.g., preference weighting).
Mobile-first design received positive feedback during beta testing. | Drill-down charts caused mobile UI crashes. | Simplify interactive chart libraries for mobile. | Simplify interactive chart libraries for mobile.
LinkedIn verification reduced fake mentor profiles. | Delays in implementing offline mode for cached data. | Prioritize offline mode in the next sprint. | Prioritize offline mode in the next sprint.