## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
Clear understanding of Sprint 1 objectives and scope related to survey ingestion and data quality. | Survey ingestion is still ongoing, so complete data validation could not be finalized. | Introduce staged ingestion checkpoints instead of waiting for full dataset completion. | Define interim cut-off dates for partial data validation and review.
Survey schema design and validation rules were finalized early in the sprint. | Minor inconsistencies found in early survey responses due to user input errors. | Add clearer survey instructions and basic client-side validation. | Update survey form with mandatory fields and validation hints.
Backend ingestion pipeline and error logging mechanism were successfully implemented. | Limited time available for extensive testing due to parallel survey collection. | Automate ingestion tests using sample datasets. | Add automated test cases to CI for ingestion scenarios.
Team coordination was effective despite a small two-member team. | Dependency on survey completion delayed analytics validation. | Parallelize work by validating existing data while new surveys are collected. | Schedule daily short syncs to re-prioritize tasks based on data availability.
Initial data quality metrics framework (completeness, duplicates) was defined. | Alerts could not be fully tuned due to incomplete data volume. | Use temporary thresholds during ingestion phase. | Reconfigure alert thresholds once survey ingestion is completed.