## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
What went well | What went poorly | What ideas do you have | How should we take action
Data quality metrics such as completeness, duplicate detection, and outlier identification were implemented successfully after batch ingestion. | Some inconsistencies in uploaded survey files caused minor issues during normalization and processing. | Introduce stricter validation rules before ingestion to reduce inconsistent inputs. | Implement a validation check for required fields and acceptable value ranges before storing records.
The monitoring dashboard was able to display batch summaries and quality metrics clearly. | Initial dashboard layout required adjustments to make the information easier to interpret. | Create simple UI wireframes before development to visualize dashboard layout. | Review dashboard design with the team before implementing UI components.
Batch tracking with unique batch IDs made it easier to trace uploaded data and monitor quality metrics. | Some test cases were not prepared early, which slowed down testing in later stages. | Prepare test datasets for normal, duplicate, and incomplete survey records in advance. | Maintain a predefined set of test datasets for future testing and validation.
Alert configuration allowed thresholds for completeness, duplicates, and outliers to be monitored automatically. | Testing alert notifications required additional setup and verification steps. | Use mock alert endpoints for faster testing during development. | Create reusable test configurations for alert channels.
Team coordination between frontend and backend tasks helped maintain steady progress throughout the sprint. | Some edge cases related to outlier detection required additional debugging. | Expand the testing scenarios to include more extreme or unexpected data values. | Add additional edge-case testing during the quality assurance phase of the sprint.