## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
Redis caching improved analytics API response time for repeated requests. | Cache configuration required several adjustments before optimal performance. | Define clear cache tuning guidelines for future development. | Establish cache TTL and invalidation strategy before implementation.
Pagination caps and rate limiting improved API stability and prevented excessive requests. | Determining the correct rate-limit values was challenging without real traffic data. | Use collected API usage statistics to refine rate-limit thresholds. | Continuously monitor request patterns and adjust limits accordingly.
Load testing helped identify performance bottlenecks in analytics endpoints. | Setting up the load testing environment required additional preparation time. | Maintain reusable load testing scripts for future sprints. | Prepare load testing environment and scripts early in the sprint.
CI pipelines successfully generated automated test coverage reports. | Some modules initially had limited test coverage. | Expand automated testing to include edge cases and failure scenarios. | Review CI coverage reports regularly and add missing tests.
Staging smoke tests ensured deployment validation before release. | Debugging smoke test failures sometimes required manual log analysis. | Improve failure logs and diagnostic messages. | Enhance smoke test reporting and integrate logs for easier troubleshooting.