## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
Mentor profile discovery feature was completed with search filters and LinkedIn integration. | Some bugs were reported in mobile dashboard navigation gestures. | More thorough mobile testing before final QA. | Create a mobile QA checklist and assign team member to test across devices.
Career interest matching algorithm showed promising accuracy. | Matching score not clearly understood by some users. | Improve clarity of matching score and add tooltip explanation. | Add in-app help text or info icons explaining score logic.
Interactive charts with drill-downs added value to dashboard usability. | Performance dropped with large datasets in drill-downs. | Optimize chart rendering and lazy-load detailed data. | Investigate and implement chart performance improvements.
UI skeleton loaders and error toasts created smoother user feedback. | Some errors were not consistently caught across pages. | Standardize error handling across components. | Implement global error handling service and audit existing flows.